## Projects
Project Name | Task | Start Date | End Date | Start to End | Start to Today | Progress | Resource | Status | Milestone
Community Park Renovation | Site Preparation (Demolition, Grading) | 2024-04-01 | 2024-04-12 | 11 | 37 | 1 | Adam | Complete
Community Park Renovation | Playground Equipment Installation | 2024-04-12 | 2024-04-19 | 7 | 26 | 1 | Jack | Complete
Community Park Renovation | Landscaping & Pathway Construction | 2024-04-19 | 2024-04-25 | 6 | 19 | 1 | John | Complete
Community Park Renovation | Park Furniture & Amenities Installation | 2024-04-25 | 2024-05-04 | 9 | 13 | 1 | David | Complete
Community Park Renovation | Final Inspections & Grand Opening (Optional) | 2024-05-04 | 2024-05-16 | 12 | 4 | 0.33333 | Sara | In Process
School Building Expansion | Foundation & Slab Construction | 2024-04-10 | 2024-04-20 | 10 | 28 | 1 | Samuel | Complete
School Building Expansion | Framing & Rough-In Work (Electrical, Plumbing, HVAC) | 2024-04-20 | 2024-04-28 | 8 | 18 | 1 | Ron | Complete
School Building Expansion | Exterior Cladding & Roofing | 2024-04-28 | 2024-05-08 | 10 | 10 | 1 | Joseph | Complete
School Building Expansion | Exterior Cladding & Roofing | 2024-05-08 | 2024-05-08 | 0 | 0 | 1 | Joseph | Complete | Exterior Done
School Building Expansion | Interior Finishing (Walls, Flooring, Ceilings) | 2024-05-08 | 2024-05-17 | 9 | 0 | 0 | Harry | Not Started
School Building Expansion | Equipment Installation & Final Inspections | 2024-05-17 | 2024-05-25 | 8 | -9 | 0 | Hanna | Not Started
Residential Roof Replacement | Permitting & Material Procurement | 2024-04-15 | 2024-04-28 | 13 | 23 | 1 | Kate | Complete
Residential Roof Replacement | Roof Tear-Off & Debris Removal (Per Roof) | 2024-04-28 | 2024-05-11 | 13 | 10 | 0.76923 | Irvin | In Process
Residential Roof Replacement | Underlayment & Shingle Installation (Per Roof) | 2024-05-11 | 2024-05-24 | 13 | -3 | 0 | Leo | Not Started
Residential Roof Replacement | Final Inspections & Clean Up (Per Roof) | 2024-05-24 06:00 | 2024-05-24 17:00 | 0.45833 | -16.25 | 1 | Marry | Complete